## project
GANTT CHART
S.No. | ACTIVITY | START | DURATION | WEEKS
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
1 | Idea Brainstroming | 1 | 1
2 | Proposal Writing | 1 | 2
3 | Learning Python | 3 | 1
4 | Research on Speech Processing and Machine Learning | 3 | 2
5 | Learning Raspberry PI operations | 4 | 1
6 | Engine Development | 5 | 2
7 | Mid-Term Presentation | 7 | 1
8 | Hardware Development | 8 | 1
9 | Debuging and Testing | 9 | 2
10 | Final Presentaion and Report Submission | 11 | 1